## Sheet1
| Initiating |  |  | Planning |  |  | Executing |  |  | Monitoring and Controlling |  |  | Closing
Integration Management | Develop Project Charter |  |  | Develop Project Management Plan |  |  | Direct & Manage Project Execution |  |  | Monitor & Control Project Work |  |  | Close Project or Phase
| Project SOW | Expert Judgement | Project Charter | Project Charter | Expert Judgement | Project Management Plan | Project Management Plan | Expert Judgement | Deliverables | Project Management Plan | Expert Judgement | Change Requests | Project Management Plan | Expert Judgement | Final product, service, or result transition
| Business Case |  |  | Outputs from Planning Processes |  |  | Approved Change Requests | PMIS | WPI | Performance Reports |  | PM Plan Updates | Accepted Deliverables
| Contract (external) |  |  | EEFs & OPAs |  |  | EEFs & OPAs |  | Change Requests | EEFs & OPAs |  | Proj Doc Updates | OPAs |  | OPAs (updates) |  | I | P | E | M&C | C
| EEFs & OPAs | [7 empty] | PM Plan Updates |  | Integrted Change Control |  |  |  |  | I | x | x | x | x | x
[9 empty] | Proj Doc Updates | [6 empty] | S |  | x |  | x
[10 empty] | Integrated Change Control | [5 empty] | T |  | x |  | x
[10 empty] | Project Management Plan | Expert Judgement | Change Request Status Updates |  |  |  | C |  | x |  | x
[10 empty] | WPI | Change Control Meetings | PM Plan Updates |  |  |  | Q |  | x | x | x
[10 empty] | Change Requests |  | Proj Doc Updates |  |  |  | HR |  | x | x
[10 empty] | EEFs & OPAs | [5 empty] | C | x | x | x | x
Scope Management |  |  |  | Collect Requirements | [5 empty] | Verify Scope | [5 empty] | R |  | x |  | x
|  |  |  | Project Charter | Interviews - Focus Groups | Requirements Documentation |  |  |  | Project Management Plan | Inspection | Accepted Deliverables |  |  |  | P |  | x | x | x | x
|  |  |  | Stakeholder Register | Facilitated Workshops | Requirements Management Plan |  |  |  | Requirements Documentation |  | Change Requests
[5 empty] | Group Creativity Techniques | Requirements Traceability Matrix |  |  |  | Requirements Traceability Matrix |  | Proj Doc Updates
[5 empty] | Group Decision-Making Techniques |  |  |  |  | Validated Deliverables
[5 empty] | Questionnaires and surveys |  |  |  |  | Control Scope
[5 empty] | Observations |  |  |  |  | Project Management Plan | Variance Analysis | Work Performance Measurements
[5 empty] | Prototypes |  |  |  |  | Scope Baseline, Config Mgmt Plan, Change Mgmt Plan, Requirements Mgmt Plan |  | OPAs (updates)
|  |  |  | Define Scope | [7 empty] | Change Requests
|  |  |  | Project Charter | Expert Judgement | Project Scope Statement |  |  |  | WPI (Work Performance Information, as opposed to Work Performance Data / WPD) |  | PM Plan Updates
|  |  |  | Requirements Documentation | Product Analysis | Proj Doc Updates |  |  |  | Requirements Documentation |  | Proj Doc Updates
|  |  |  | OPAs | Alternatives Identification | Stakeholder Register, Requirements Documentation, Requirements Traceability Matrix |  |  |  | Requirements Traceability Matrix
Facilitated Workshops
Create WBS
|  |  |  | Project Scope Statement | Decomposition | WBS
|  |  |  | Requirements Documentation |  | WBS Dictionary
|  |  |  | OPAs |  | Scope Baseline
Proj Doc Updates
Time Management |  |  |  | Define Activities | [5 empty] | Control Schedule
|  |  |  | Scope Baseline | Decomposition | Acvity List |  |  |  | Project Management Plan | Performance Reviews | Work Performance Measurements
|  |  |  | EEFs & OPAs | Rolling Wave Planning | Activity Attributes |  |  |  | Project Schedule | Variance Analysis | OPAs (updates)
[5 empty] | Templates | Milestone List |  |  |  | WPI | PM Software | Change Requests
[5 empty] | Expert Judgement |  |  |  |  | OPAs | Resource Leveling | PM Plan Updates
|  |  |  | Sequence Activities | [6 empty] | What-If Scenario Analysis | Proj Doc Updates
|  |  |  | Activity List | Precendence Diagram. Method (et. al.) | Project Schedule Network Diagrams |  |  |  |  | Adjusting Leads and Lags
|  |  |  | Activity Attributes | Dependency Determination | Proj Doc Updates |  |  |  |  | Schedule Compression
|  |  |  | Milestone List | Applying Leads/Lags | [5 empty] | Scheduling Tool
|  |  |  | Project Scope Statement | Schedule Network Templates
OPAs
Estimate Activity Resources
|  |  |  | Activity List | Expert Judgement | Activity Resource Requirements
|  |  |  | Activity Attributes | Alternatives Analysis | Resource Breakdown Structure
|  |  |  | Resource Calendars | Published Estimating Data | Proj Doc Updates
|  |  |  | EEFs & OPAs | Bottom-Up Estimating
Project Mgmt Software
Estimate Activity Durations
|  |  |  | Activity List | Expert Judgement | Activity Duration Estimates
|  |  |  | Activity Attributes | Analogous Estimating | Activity Attributes (updates)
|  |  |  | Activity Resource Requirements | Parametric Estimating
|  |  |  | Resource Calendars | Three-Point Estimates
|  |  |  | Project Scope Statemnt | Reserve Analysis
EEFs & OPAs
Develop Schedule
|  |  |  | Activity List | Schedule Network Analysis | Project Schedule
|  |  |  | Activity Attributes | Critical Path Method | Schedule Baseline
|  |  |  | Project Schedule Network Diagrams | Critical Chain Method | Schedule Data
|  |  |  | Resource Requirements | Resource Leveling | Proj Doc Updates
|  |  |  | Resource Calendars | What-If Analysis (Monte Carlo)
|  |  |  | Duration Estimates | Applying Leads/Lags
|  |  |  | Project Scope Statement | Schedule Compression
|  |  |  | EEFs & OPAs | Scheduling Tool
Cost Management |  |  |  | Estimate Costs | [5 empty] | Control Costs
|  |  |  | Scope Baseline | Expert Judgement | Activity Cost Estimates |  |  |  | Project Management Plan | EVM | Work Perf. Measurements
|  |  |  | Project Schedule | Analogous Estimating | Basis of Estimates |  |  |  | Cost Baseline, Cost Management Plan | Forecasting | Budget Forecasts
|  |  |  | Human Resource Plan | Parametric Estimating | Proj Doc Updates |  |  |  | Funding Requirements | TCPI (To-Complete Performance Index) | OPAs (updates)
|  |  |  | Risk Register | Bottom-Up Estimating |  |  |  |  | WPI | Performance Reviews | Change Requests
|  |  |  | EEFs & OPAs | Three-Point Estimates |  |  |  |  | OPAs | Variance Analysis | PM Plan Updates
[5 empty] | Reserve Analysis | [5 empty] | PM Software | Proj Doc Updates
Cost of Quality
PM Estimating Software
Vendor Bid Analysis
Determine Budget
|  |  |  | Activity Cost Estimates | Cost Aggregation | Cost Performance Baseline
|  |  |  | Basis of Estimates | Reserve Analysis | Project Funding Requirements
|  |  |  | Scope Baseline | Expert Judgement | Proj Doc Updates
|  |  |  | Project Schedule | Historical Relationships
|  |  |  | Resource Calendars | Funding Limit Reconciliation
Contracts
OPAs
Quality Management |  |  |  | Plan Quality |  |  | Perform Quality Assurance |  |  | Perform Quality Control
|  |  |  | Scope Baseline | Cost-Benefit Analysis | Quality Management Plan | Project Management Plan | Plan quality and perform quality control techniques | OPAs Updates | Project Management Plan | Cause & Effect Diagrams | Quality Control Measurements
|  |  |  | Stakeholder Register | Cost of Quality | Quality Metrics | Quality Metrics | Quality Audits | Change Requests | Quality Metrics | Control Charts | Validated Changes
|  |  |  | Cost Perf.Baseline | Control Charts | Quality Checklists | WPI | Proecss Analysis | PM Plan Updates | Quality Checklists | Flowcharting | Validated Deliverables
|  |  |  | Schedule Baseline | Benchmarking | Process Improvement Plan | Quality Control Measurements |  | Proj Doc Updates | Work Performance Measurements | Histogram | OPAs (updates)
|  |  |  | Risk Register | Design of Experiments | Proj Doc Updates |  |  |  | Approved Change Requests | Pareto Chart | Change Requests
|  |  |  | EEFs & OPAs | Statistical Sampling |  |  |  |  | Deliverables | Run Chart | PM Plan Updates
[5 empty] | Flowcharting |  |  |  |  | OPAs | Scatter Diagram | Proj Doc Updates
[5 empty] | Prorietary QM Methods | [5 empty] | Statistical Sampling
[5 empty] | Additional Tools | [5 empty] | Inspection
Approved Change Requests
Human Resource Management |  |  |  | Develop Human Resource Plan |  |  | Acquire Project Team
|  |  |  | Activity Resource Requirements | Org Charts & Position Descriptions | Human Resource Plan | PM Plan (Human Resource Plan) | Pre-Assignment | Project Staff Assignments
|  |  |  | EEFs & OPAs | Networking |  | EEFs & OPAs | Negotiation | Resource Calendars
[5 empty] | Organizational Theory |  |  | Acquisition | PM Plan Updates
Virtual Teams
Develop Project Team
[7 empty] | Project Staff Assignments | Interpersonal Skills | Team Performance Assessments
[7 empty] | Project Management Plan | Training | EEFs Updates
[7 empty] | Resource Calendars | Team-Building Activities
Ground Rules
Co-Location
Recognition & Rewards
Manage Project Team
[7 empty] | Project Staff Assignments | Observation and Conversation | EEFs Updates
[7 empty] | Project Management Plan | Project Performance Appraisals | OPAs Updates
[7 empty] | Team Perf. Assessments | Conflict Management | Change Requests
[7 empty] | Performance Reports | Issue Log | PM Plan Updates (HR Plan)
[7 empty] | OPAs | Interpersonal Skills
Communications Management | Identify Stakeholders |  |  | Plan Communications |  |  | Distribute Information |  |  | Report Performance
| Project Charter | Stakeholder Analysis | Stakeholder Register | Stakeholder Register | Communications Requirements Analysis | Communications Management Plan | PM Plan (Comm) | Communication Methods | OPAs | Project Management Plan | Variance Analysis | Performance Reports
| Procurement Documents | Expert Judgement | Stakeholder Management Strategy | Stakeholder Management Strategy | Communications Technology | Proj Doc Updates | Performance Reports | Information Distribution Tools |  | WPI | Forecasting Methods | OPAs (updates)
| EEFs & OPAs |  |  | EEFs & OPAs | Communications Models |  | OPAs |  |  | Work Perf. Measuremnts | Communication Methods | Change Requests
[5 empty] | Communications Methods |  |  |  |  | Budget Forecasts | Reporting Systems
OPAs
Manage Stakeholder Expectations
[7 empty] | Stakeholder Register | Communications Methods | OPAs Updates
[7 empty] | Stakeholder Mgmt Strategy | Interpersonal Skills | Change Requests
[7 empty] | PM Plan (Comm) | Management Skills | PMPlan Updates
[7 empty] | Issue Log |  | Proj Doc Updates
Change Log
OPAs
Risk Management |  |  |  | Plan Risk Management | [5 empty] | Monitor and Control Risks
|  |  |  | Project Scope Statement | Planning Meetings and Analysis | Risk Management Plan |  |  |  | Risk Register | Risk Reassessment | Risk Register Updates
|  |  |  | Cost Management Plan | [5 empty] | Project Management Plan | Risk Audits | OPAs Updates
|  |  |  | Schedule Management Plan | [5 empty] | WPI | Variance and Trend Analysis | Change Requests
|  |  |  | Communications Management Plan | [5 empty] | Performance Reports | Technical Performance Measurement | PM Plan Updates
|  |  |  | EEFs & OPAs | [6 empty] | Reserve Analysis | Proj Doc Updates
|  |  |  | Identify Risks | [6 empty] | Status Meetings
|  |  |  | Risk Management Plan | Documentation Reviews | Risk Register
|  |  |  | Activity Cost Estimates | Information-Gathering Techniques
|  |  |  | Activity Duration Estimates | (Brainstorming, Delphi)
|  |  |  | Scope Baseline | Checklist Analysis
|  |  |  | Stakeholder Register | Assumptions Analysis
|  |  |  | Cost, Sched., Quality Mgmt Plans | Diagramming Techniques
|  |  |  | Project Documents | Cause-Effect Diagrams, Flowcharts
|  |  |  | EEFs & OPAs | SWOT Analysis
Expert Judgement
Qualitative Risk Analysis
|  |  |  | Risk Register | Risk Probability and Impact Assessment | Risk Register Updates
|  |  |  | Risk Management Plan | Probability and Impact Matrix | ranking by priority, categorization, urgent risks, trends, watchlist, further analysis list
|  |  |  | Project Scope Statement | Risk Data Quality Assessment
|  |  |  | OPAs | Risk Categorization
Risk Urgency Assessment
Expert Judgement
Quantitative Risk Analysis
|  |  |  | Risk Register | Data Gathering and Representation Techniques | Risk Register Updates
|  |  |  | Risk Management Plan | Quantitative Risk Analysis and Modeling Techniques | prioritized list of quantified risks, trends in quantitative risk analysis results, probabilistic analysis of project
|  |  |  | Cost Management Plan | EMV, Modeling & Simulation, Sensitivity Analysis, Decision Tree Analysis
|  |  |  | Schedule Mgmt Plan | Expert Judgement
OPAs
Plan Risk Responses
|  |  |  | Risk Register | Strategies for Negative Risks or Threats | Risk Register Updates
|  |  |  | Risk Management Plan | mitigate, avoid, transfer, accept | Risk Response Plans, Risk Owners & Responsibilities, Risk Triggers, Budget for Response Strategies, Residual Risks, Secondary Risks, Contingency Reserves, Fallback Plans
[5 empty] | Strategies for Positive Risks or Opportunities | Risk-Related Contract Decisions
[5 empty] | share, exploit, enhance, accept | Risk Management Plan Updates
[5 empty] | Contingent Response Strategies | Proj Doc Updates
Expert Judgement
Procurement Management |  |  |  | Plan Procurements |  |  | Conduct Procurements |  |  | Administer Procurements |  |  | Close Procurements
|  |  |  | Scope Baseline | Make-or-Buy Analysis | Procurement Management Plan | Project Management Plan | Bidder Conferences | Selected Sellers | Procurement Documents | Contract Change Control System | Procurement Documentation | PM Plan (Procurement) | Procurement Audits | Closed Procurements
|  |  |  | Requirements Documentation | Expert Judgement | Procurements SOWs | Procurement Documents | Proposal Evaluation Technique | Procurement Contract Award | PM Plan (Procurement) | Procurement Performance Reviews | OPAs Updates | Procurement Documentation | Negotiated Settlements | OPAs (updates)
|  |  |  | Teaming Agreements | Contract Types | Make-or-Buy Decisions | Source Selection Criteria | Independent Estimates | Resource Calendars | Contract | Inspection and Audits | Change Requests |  | Records Mgmt. Sys.
|  |  |  | Risk Register |  | Procurement Documents | Qualified Seller List | Expert Judgement | Change Requests | Performance Reports | Performance Reporting | PM Plan Updates
|  |  |  | Risk-Related Contract Decisions |  | Source Selection Criteria | Seller Proposals | Advertising | PM Plan Updates | Approved Change Requests | Payment Systems | Procurement Mgmt. Plan, Baseline Schedule
|  |  |  | Activity Resource Requirements |  | Change Requests | Project Documents | Internet Search | Proj Doc Updates | WPI | Claims Administration
|  |  |  | Project Schedule |  |  | Make-or-Buy Decisions | Procurement Negotiation |  |  | Records Management System
|  |  |  | Activity Cost Estimates |  |  | Teaming Agreements
|  |  |  | Cost Performance Baseline |  |  | OPAs
EEFs & OPAs